## AGX-Orin
Project | Test Image Version | OS | JetPack6.1
AFE-R750 EVT | afer750a1_ubuntu22.04-jp6.1_v5.0.0_kernel-5.15.148_agx-orin+orin-nx_agx-64g-32g+nx-16g_emmc+nvme+usb_2025-12-01.tgz | Ubuntu22.04 | Linux36.4 / Kernel5.15
No | Module | Bridge | Port | Test Item | Test Steps | Owner | Result | Result Comment | deadline
1 | DEBUG UART |  | COM3 | TI MAX3221 RS232 TRANSCEIVE | System output and input | RAY | PASS | OK (12/16 OK)
2 | USB2.0 (TYPE-C) (flash image port only) |  |  |  | For USB Recovery mode | RAY | PASS | OK (12/16 OK)
3 | HDMI |  |  |  |  | RAY | ISSUE | 2025-12-31
4 | AT MODE on / off test | [5 empty] | PASS | 1820 TIMES
5 | FAN CTRL |  |  |  |  | RAY | PASS | OK
6 | DB9 | TI THVD4431 | COM1 - RS232 | Send/Receive pattern to host PC |  | RAY | PASS | OK (12/30)
|  |  | COM1 - RS422 | Send/Receive pattern to host PC |  | RAY | PASS | OK (1/19)
|  |  | COM1 - RS485 | Send/Receive pattern to host PC |  | RAY | PASS | OK (1/20)
|  |  | COM2 - RS232 | Send/Receive pattern to host PC |  | RAY | PASS | OK (1/17)
|  |  | COM2 - RS422 | Send/Receive pattern to host PC |  | RAY | PASS | OK (1/19)
|  |  | COM2 - RS485 | Send/Receive pattern to host PC |  | RAY | PASS | OK
7 | DIO 16bit | TI TCA9555 | I2C2 | loop back / set direction (in/out) |  | RAY | PASS | (1/20) GPIO expender OK
8 | I2C |  | I2C2~5 |  |  | RAY | PASS | OK (1/22) I2C2 / I2C/3 / I2C5
9 | TPM | NPCT760AABYX | I2C5 |  |  | RAY | PASS | OK (1/22)
10 | Terminal block | TI_ISO1044BDR (CAN transceivers _isolation) | CAN0 CAN1 | read/write |  | RAY | PASS | FUNCTION PASS
11 | USB2.0 | ASMEDIA ASM2074 | Port1 | USB disk write/read/verify pattern |  | RAY | PASS | READ/WRITE pass (12/18 OK) / SI pattern pass
|  |  | Port2 | USB disk write/read/verify pattern |  | RAY | PASS | READ/WRITE pass (12/18 OK) / SI pattern pass
|  |  | Port3 | USB disk write/read/verify pattern |  | RAY | PASS | READ/WRITE pass (12/18 OK) / SI pattern pass
|  |  | Port4 | USB disk write/read/verify pattern |  | RAY | PASS | READ/WRITE pass (12/18 OK) / SI pattern pass
12 | USB3.0 | ASMEDIA ASM2074 | Port1 | USB disk write/read/verify pattern |  | RAY | PASS | READ/WRITE pass (12/18 OK) / SI pattern FW cover
|  |  | Port2 | USB disk write/read/verify pattern |  | RAY | PASS | READ/WRITE pass (12/18 OK) / SI pattern FW cover
|  |  | Port3 | USB disk write/read/verify pattern |  | RAY | PASS | READ/WRITE pass (12/18 OK) / SI pattern FW cover
|  |  | Port4 | USB disk write/read/verify pattern |  | RAY | PASS | READ/WRITE pass (12/18 OK) / SI pattern FW cover
13 | I226-LM (2.5G) | PCIE SWITCH ASMEDIA ASM2806 PC | LAN1 | Connect to network / FW /MAC ADDRESS |  | RAY | PASS | FW/MAC PASS (12/17 OK)
|  |  | LAN2 | Connect to network / FW /MAC ADDRESS |  | RAY | PASS | FW/MAC PASS (12/17 OK)
|  |  | LAN3 | Connect to network / FW /MAC ADDRESS |  | RAY | PASS | FW/MAC PASS (12/17 OK)
|  |  | LAN4 | Connect to network / FW /MAC ADDRESS |  | RAY | PASS | FW/MAC PASS (12/17 OK)
14 | NVME (PCIE X4) |  | M.2 Key-M | storage |  | RAY | PASS | read/write/ GEN4 OK (12/20 OK)
15 | WIFI (PCIE X1) +USB2 | AIW-170BQ | M.2 Key-E | connect to net work |  | RAY | PASS | PASS (1/10)
16 | GNSS (USB2) | AIW-210XU-001 | M.2 Key-B | GPS / PPS signal |  | RAY | PASS | PASS (1/8)
17 | Cellular (USB3) | AIW-357DK-G2U | M.2 Key-B | 5G |  | RAY | PASS | PASS (1/8)
18 | Nano Sim (USB3) | AIW-357DK-G2U | M.2 Key-B | 5G |  | RAY | PASS | PASS (1/8)
19 | IMU BMI088 (MAIN) |  | I2C2 |  |  | RAY | PASS | 2025-03-04
20 | GMSL CAMERA 8組 otobrite | otobrite camera | I2C3 / I2C5 |  |  | RAY | PASS | 4/15 8CAMERA OK
21 | MTI-3 MOVELLA (IMU OPTIONAL) |  | UART |  |  | RAY | PASS | 4/16 已可以收錄資料 ; 後續細節確認中
22 | TIME SYNC | GPS/IMU BMI088/ LIDAR/CAMERA | [5 empty] | 4/30 DEVICE 端 TIME SYNC VIEWER GNSS/系統 時間整合
| Orbbec Gemini 335Lg | [5 empty] | PASS
AGX SKU

## ORIN NX
Project | Test Image Version | OS | JetPack6.1
AFE-R750 EVT | afer750a1_ubuntu22.04-jp6.1_v5.0.0_kernel-5.15.148_agx-orin+orin-nx_agx-64g-32g+nx-16g_emmc+nvme+usb_2025-12-01.tgz | Ubuntu22.04 | Linux36.4 / Kernel5.15
No | Module | Bridge | Port | Test Item | Test Steps | Owner | Result | Result Comment | deadline
1 | DEBUG UART |  | COM3 | TI MAX3221 RS232 TRANSCEIVE | System output and input | RAY | PASS | 2025-03-04
2 | USB2.0 (TYPE-C) (flash image port only) |  |  |  | For USB Recovery mode | RAY | PASS | 2025-03-04
3 | HDMI |  |  |  |  | RAY | PASS
4 | AT MODE on / off test |  |  |  |  | RAY | PASS
5 | FAN CTRL |  |  |  |  | RAY | PASS | 2025-03-04
6 | DB9 | TI THVD4431 | COM1 - RS232 | Send/Receive pattern to host PC |  | RAY | PASS | 2025-03-04
|  |  | COM1 - RS422 | Send/Receive pattern to host PC |  | RAY | PASS | 2025-03-14
|  |  | COM1 - RS485 | Send/Receive pattern to host PC |  | RAY | PASS | 2025-03-14
|  |  | COM2 - RS232 | Send/Receive pattern to host PC |  | RAY | PASS | 2025-03-04
|  |  | COM2 - RS422 | Send/Receive pattern to host PC |  | RAY | PASS | 2025-03-14
|  |  | COM2 - RS485 | Send/Receive pattern to host PC |  | RAY | PASS | 2025-03-14
7 | DIO 16bit | TI TCA9555 | I2C2 | loop back / set direction (in/out) |  | RAY | PASS | 2025-03-07
8 | I2C |  | I2C2~5 |  |  | RAY | PASS | 2025-03-04
9 | TPM | NPCT760AABYX | I2C5 |  |  | RAY | PASS | 3月11日
10 | Terminal block | TI_ISO1044BDR (CAN transceivers _isolation) | CAN0 | read/write |  | RAY | PASS | 3月11日
11 | USB2.0 | ASMEDIA ASM2074 | Port1 | USB disk write/read/verify pattern |  | RAY | PASS | 2025-03-04
|  |  | Port2 | USB disk write/read/verify pattern |  | RAY | PASS | 2025-03-04
|  |  | Port3 | USB disk write/read/verify pattern |  | RAY | PASS | 2025-03-04
|  |  | Port4 | USB disk write/read/verify pattern |  | RAY | PASS | 2025-03-04
12 | USB3.0 | ASMEDIA ASM2074 | Port1 | USB disk write/read/verify pattern |  | RAY | PASS | 2025-03-04
|  |  | Port2 | USB disk write/read/verify pattern |  | RAY | PASS | 2025-03-04
|  |  | Port3 | USB disk write/read/verify pattern |  | RAY | PASS | 2025-03-04
|  |  | Port4 | USB disk write/read/verify pattern |  | RAY | PASS | 2025-03-04
13 | I226-LM (2.5G) | PCIE SWITCH ASMEDIA ASM2806 PC | LAN1 | Connect to network / FW /MAC ADDRESS |  | RAY | PASS | 2025-03-04
|  |  | LAN2 | Connect to network / FW /MAC ADDRESS |  | RAY | PASS | 2025-03-04
|  |  | LAN3 | Connect to network / FW /MAC ADDRESS |  | RAY | PASS | 2025-03-04
|  |  | LAN4 | Connect to network / FW /MAC ADDRESS |  | RAY | PASS | 2025-03-04
14 | NVME (PCIE X4) |  | M.2 Key-M | storage |  | RAY | PASS | 2025-03-04
15 | WIFI (PCIE X1) +USB2 |  | M.2 Key-E | connect to net work |  | RAY | PASS | 2025-03-04
16 | GNSS (USB2) | AIW-210XU-001 | M.2 Key-B | GPS / PPS signal |  | RAY | PASS | 2025-03-04
17 | Cellular (USB3) | AIW-357DK-G2U | M.2 Key-B | 5G |  | RAY | PASS | 2025-03-14
18 | Nano Sim (USB3) | AIW-357DK-G2U | M.2 Key-B | 5G |  | RAY | PASS | 2025-03-14
19 | IMU BMI088 (MAIN) |  | I2C2 |  |  | RAY | PASS | 2025-03-21
20 | GMSL CAMERA 4組 otobrite | otobrite | mipi-CSI I2C5 |  |  | RAY | PASS | 2025-04-28
21 | TIME SYNC | GPS/IMU BMI088/ LIDAR/CAMERA | [5 empty] | 4/30 DEVICE 端 TIME SYNC VIEWER GNSS/系統 時間整合
| Orbbec Gemini 335Lg | [5 empty] | PASS
ORIN NX SKU

## SI TEST TOOL 表格
SI TEST ITEM | Port | scirpt/FW | SI test command | POR | Note
HDMI | HDMI1 |  | V | HDMI_1x 1.4a, 4K 24Hz
USB3.2 | LAN1_USB12 (2PORT) | ASM2704 FW (enable compliance) 230830_15_00_00.bin | 示波器直接切CP0~CP15 | USB3.2 GEN2 (10G) | # sudo ./find307x -x
| LAN2_USB34 (2PORT) | ASM2704 FW (enable compliance) 230830_15_00_00.bin | 示波器直接切CP0~CP15 | USB3.2 GEN2 (10G)
| M2B1 | usb_hub_compliance_test | V | USB3.2 GEN1 (5G) | 參考附件WORD 打開USB3 COMPLIANCE MODE
USB2 | LAN1_USB12 (2PORT) | 307x_Linux_Tool_20241111 | V | USB2 | 桌面上有一個ASM2074資料夾; 需使用CONSOLE ; 下指令。 # sudo ./find307x -f 4 下完指令後; 每一PORT 會有5分鐘 打PATTERN ; 然後回復可使用USB 的狀態
| LAN2_USB34 (2PORT) | 307x_Linux_Tool_20241111 | V | USB2
| M2E1 | usb_hub_compliance_test | V | USB2 | 參考附件WORD 打開USB2 COMPLIANCE MODE
| M2B1 | usb_hub_compliance_test | V | USB2
LAN | LAN1_USB12 (LAN1) | script @RAY 請與原作確認 | V | AGX ORIN :2.5G ORIN NX :1G | 1G/2.5G test command with sript 100M link partner 治具
| LAN2_USB34 (LAN2) | script @RAY 請與原作確認 | V | AGX ORIN :2.5G ORIN NX :1G
| LAN34 (LAN34) | script @RAY 請與原作確認 | V | AGX ORIN :2.5G ORIN NX :1G
PCIE | M2B1 | script image.zip | V |  | 不需COMMAND ; 直接上治具 即可測試 (待SI 安排實驗時間)
| M2E1 | script image.zip | V
| M2M1 | script image.zip | V

## SI-PV test status
NX
SI 測項 | 量測日 | 完成 |  | SI 測項 | 量測日 | 完成
Power sequence | 1/14~1/15 | 1/14 | issue :已解 | Power sequence | 3/7 | 3/7 | PASS
Clock waveform | 1/16~1/17 | 1/16 | PASS | Clock waveform | 3/13 | 3/13 | PASS
USB2.0的droop/drop | 1/20 | 1/20 | PASS | PCIe Gen1-4 | 3/12 GEN1 ~GEN3 3/28 GEN4 M2 . Mkey 待排 | 3/12 3/14 | PASS PASS
LAN 1000/100 | 1/21 | 1/21 | PASS | HDMI1.4 | 3/11 | 3/11 | PASS
USB2.0 eye | 1/22 | 1/20 | PASS
LAN 2.5G | 1/23~2/3 | 2/3 | PASS
HDMI1.4 | 2/4 | 2/4 | PASS
USB3.2 gen1/2 | 2/5 | 2/12 (ASMEDIA 提供新U3 TOOL FOR TEST) 2/13 test FAIL 2/14 寄送ASMEDIA DEBUG TUNING (solution : 調高 1.05V --> 1.12V) 2/26 安排另外兩片板子WITH NEW IMAGE 實驗是否為單板問題。 2/28 DEBUG PASS | DEBUG PASS
PCIe Gen1-4 | 2/6~2/7 | 1/20 (已排空檔完成 GEN1~GEN3) 2/5 GEN4 PASS | PASS
PV test | 1/24 finish 100% | The PU7 5V_AO of MOSFET_VGS_VDS_Voltage test results did not conform to the specification. | issue : 4257006 2/5 debug PASS

## LAB
shock/Vibration | 3/31~4/1 | PASS
-15C power on/off 1000times | 4/8~4/10 | FAIL (待SW 下SOLUTION 關機CPU LOG 太久) AT : PASS ATX : FAIL (NVBUG ID 5221140 )
65C power on/off 1000times | 4/11~4/14 | FAIL (待SW 下SOLUTION 關機CPU LOG 太久) AT : PASS ATX : FAIL (NVBUG ID 5221140 )
-15C operation 24hours | 4/14~4/15 | PASS
40C 95% humidity operation 48 hours | 4/15~4/17 | PASS
60C operation 24 hours | 4/17~4/18 | PASS
THERMAL PROFILE | 4/23~4/24 | ON GOING