## Slide 1: LEO –D series
WISE-EC
Embedded Core Group
5th ,Dec, 2017
project status

## Slide 2: Outline
Project Planed Schedule
Marketing Planning
HW Status
  D33/53
  D73
  WISE-1541/1841
  WISE-DB1503/1504
SW Status
  Device mgt
  Service mgt
  Account mgt
  外部資料交換介面
  Image generator

## Slide 3: HW/SW Schedule
Dec. 2017
D33/53 layout, EVT 12/8th Pro.
Jan 2018
D73 EVT 1/4th Pro.
Feb 2018
D33/53 DVT Pro.
March 2018
April 2018
June 2018
D73 Design
WISE-1541 Sample Pro.
WISE-1541 Design
WISE-1841 Design
WISE-1841 Sample Pro.
D33/53 DVT design
D73 DVT design
D series Cert. Pre-scan
D73 DVT Pro.
WISE-DB1503 Design (D53 EVK)
WISE-DB1503 Pro.
WISE-1841 DVT Design
WISE-DB1504 Design (D73 EVK)
WISE-1841 DVT Pro.
WISE-DB1504 Pro.
D33/53 PVT
D73 PVT
July 2018
WISE-1541 DVT
WISE-1841 PVT
D33/53 MP
D73 MP
WISE-1841 MP
Device Side
SW feature completed
Connecting 400 Tags
Connecting 1200 Tags
Connecting 3000 Tags
SW Solution Development
Alpha Test & Bug Fixing
Beta Test & Bug Fixing
Release

## Slide 4: Outline
Project Planed Schedule
Marketing Planning
HW Status
  D33/53
  D73
  WISE-1541/1841
  WISE-DB1503/1504
SW Status
  Device mgt
  Service mgt
  Account mgt
  外部資料交換介面
  Image generator

## Slide 5: SW RD WISE-PaaS Task Planning
Type | Group | Function | Owner | Start | End | Status
WISE-PaaS/ESL | ESL Portal | Layout adjust | Dylan | 2017/11/20 | 2017/11/24 | N
 |  | Static prototype of ESL Management System | Dylan | 2017/11/27 | 2017/11/30 | N
 | Barcode reader link | android app | Dylan | 2017/11/9 | 2017/11/17 | N
 | ESL List | Hierarchy structure display of GW / Router / Tag | Dylan | 2017/12/4 | 2017/12/8 | N
 |  | Retrieve basic info, link and transmission status ( Simulator ) | Eric | 2017/11/13 | 2017/11/17 | Y
 |  | Image preview - vendor will provide java lib | Charles | 2017/11/27 | 2017/11/29 | N
 |  | link with item, template | Dylan | 2017/12/11 | 2017/12/15 | N
 |  | Image transmission manually | Dylan | 2017/12/18 | 2017/12/22 | N
 | Template Editor | Define a set of elements to design template ( follow medical ) | Dylan | 2017/12/25 | 2017/12/26 | N
 |  | Template operation | Dylan | 2017/12/27 | 2018/1/5 | N
 |  | Template import / export | Dylan | 2018/1/8 | 2018/1/9 | N
 |  | Icon, image, font … maintain ==> only text, icon | Dylan | 2018/1/10 | 2018/1/11 | N
 | Image Creator | image format and restrictio=> vendor will provide | Charles |  |  | N
 |  | Image creator according to ESL template and item data | Alex | 2017/12/25 | 2018/1/12 | N
 | Transmission schedule | Add a transmission schedule layout same with power management | Dylan | 2018/1/15 | 2018/1/17 | N
 |  | Transmission operation, status | Dylan | 2018/1/18 | 2018/1/19 | N
 | DataBase Design | Item Table | Alex | 2017/11/13 | 2017/11/17 | N
 |  | Template Table | Alex | 2017/11/13 | 2017/11/17 | N
 | RestfulAPI Design | Item add/edit/delete | Alex | 2017/11/20 | 2017/12/1 | N
 |  | Template add/edit/delete | Alex | 2017/12/4 | 2017/12/15 | N
 |  | Item and Template mapping API | Alex | 2017/12/18 | 2017/12/22 | N
 |  | Set image to tag | Alex | 2018/1/1 | 2018/1/12 | N
 | Installer | Server installer | TY |  |  | N

## Slide 6: Device Management (Spec.1/5 )
系統管理
  Gateway\Router\Tag狀態監控
    Tag 電量
    裝置類型
    裝置資訊(Mac address, IP address )
    Firmware Version
    RSSI
    連線狀態
    拓樸架構
    最後更新時間
    Preview Tag上的image
  Gateway\Router\Tag參數設定
    Tag Report 週期
    Tag Data Request 週期
    事件逾時參數
  Tag 註冊\移除
    Tag list import / modify
    Tag 綁定Item\解除綁定Item
    Tag 上顯示的資訊會與已存在的該位置的實物呼應，例如:Tag 顯示貨架上的某商品的價格、Tag 顯示病床上病人的資訊，在之後的敘述以”Item”代表此實物
提供易於手持裝置上使用的操作介面，例如APP 或 Mobile Web
  Item 的資料管理
密鑰管理/License 管理
Report
  活動紀錄
  更新成功率
  電池壽命分布比率

## Slide 7: Service Management (Spec.2/5 )
Image update
  事件觸發更新image
    例如後臺價格更新或是人員手動更新…
  排程更新image
    例如於促銷時間將tag 更新至新價格
  管理Tag 對應的template
  失敗重傳機制
FOTA
  Firmware 匯入介面
  排程更新firmware

## Slide 8: Account management (Spec.3/5 )
User management
  權限管控
  User 新增\刪除\修改

## Slide 9: ESL Server 外部資料交換介面 (Spec.4/5 )
外部資料交換介面
  檔案交換介面
  資料庫交換介面
  依客戶需求客製化資料交換介面
  更新ESL資料與排程

## Slide 10: Image Generator (Spec.5/5 )
Image creator
  根據將欲顯示的數值帶入Template 產生圖片
Template editor
  提供圖形化介面讓客戶可以透過拖拉元件的方式，設計並產生所需的Template file

## Slide 11
Thank You.